WEEK 1: PROJECT PLANNING AND STRATEGY FOR ML PIPELINE

Table of Contents

1. Introduction	1

2. Literature Review	3

2.1 Overview of Recommendation Systems	3

2.2 Collaborative Filtering	3

2.3 Content-Based Filtering	3

2.4 Hybrid Recommendation Systems	4

2.5 Evaluation Metrics	5

2.6 MLOps and Production ML	5

3. Problem Statement	6

3.1 Core Problem	6

3.2 Inputs	6

3.3 Potential Challenges	7

3.4 Expected Outcomes	7

4. Project Objectives	8

5. Scope and Deliverables	9

5.1 In-Scope	9

5.2 Out-of-Scope	9

5.3 Deliverables	9

6. Detailed Timeline and Phased Approach	11

7. Key Milestones	16

8. Resource Requirements	17

8.1 Software and Libraries	17

8.2 Computational Resources	18

8.3 Data Resources	18

8.4 Human Resources	18

9. Risk Management	19

9.1 Risk Identification and Mitigation	19

9.2 Risk Monitoring Plan	21

10. Strategic Roadmap for Implementation	22

10.1 Phased Implementation Strategy	22

10.2 Key Technical Decisions	22

10.3 Success Metrics	23

11. Success Criteria and Evaluation Metrics	24

11.1 Technical Success Criteria	24

11.2 Academic Evaluation Criteria	24

12. Conclusion	25

13. References	26

# 1. Introduction

The rapid growth of e-commerce platforms and digital content services has created an overwhelming abundance of choices for consumers, making it increasingly difficult for users to discover relevant products, movies, or content. Recommendation systems have emerged as a critical solution, enabling personalized user experiences that drive engagement, retention, and revenue. These systems analyze user behavior, preferences, and item characteristics to suggest items that a user is likely to find valuable.

Real-World Context:

- Amazon reports that 35% of its total sales come from its recommendation engine

- Netflix estimates that its recommendation system saves the company $1 billion annually through reduced churn

- Spotify's Discover Weekly playlist, powered by hybrid recommendations, has over 40 million weekly active users

This Project:
This project aims to design and implement a comprehensive end-to-end Machine Learning pipeline for a Hybrid Recommendation System using the MovieLens 100K dataset. The system will combine collaborative filtering and content-based filtering techniques to leverage the strengths of both approaches while mitigating their individual limitations.

Dataset Details:

- 100,000 ratings from 943 users on 1,682 movies

- Rating scale: 1-5 (integer values)

- Time period: September 1997 - April 1998

- Sparsity: 93.7% (only 6.3% of possible user-item pairs have ratings)

- Contains user demographics (age, gender, occupation) and movie metadata (genres, release date)

Collaborative filtering excels at capturing user-item interaction patterns but suffers from the cold-start problem, while content-based filtering effectively handles new items but can create filter bubbles by recommending overly similar content.

The project will be executed over a 6-week period (August 14, 2026 – September 25, 2026) as part of a mandatory academic summer internship. The deliverables include a fully functional ML pipeline, a deployed REST API, comprehensive documentation, and a detailed project report.

Significance:
By building a hybrid recommendation system, this project showcases the ability to:

- Integrate multiple ML techniques (SVD + TF-IDF + XGBoost)

- Handle large-scale data (100,000+ interactions)

- Implement production-grade APIs (FastAPI + Streamlit)

- Apply modern MLOps practices (MLflow + ZenML + Docker)

# 2. Literature Review

## 2.1 Overview of Recommendation Systems

Recommendation systems have become a cornerstone of modern digital platforms. The fundamental goal is to predict user preferences and suggest items that align with their interests.

Market Impact:

- Amazon: 35% of revenue from recommendations

- Netflix: 80% of watched content from recommendations

- YouTube: 70% of watch time from recommendations

## 2.2 Collaborative Filtering

Collaborative filtering (CF) operates on the principle that users who have agreed in the past will agree in the future.

Types of CF:

- User-based CF: Finds similar users based on rating patterns (Resnick et al., 1994)

- Item-based CF: Finds similar items based on user ratings (Sarwar et al., 2001)

- Matrix Factorization: Decomposes user-item matrix into latent factors; SVD and ALS are most effective (Koren et al., 2009)

Success Story:
The Netflix Prize (2006-2009) offered $1 million to improve recommendation accuracy by 10%. The winning solution used an ensemble of 107 different CF models, achieving 10.06% improvement through matrix factorization techniques.

Limitations:

- Cold-start problem (cannot recommend new items or to new users)

- Data sparsity (most user-item pairs have no ratings)

- Popularity bias (recommends only popular items)

## 2.3 Content-Based Filtering

Content-based filtering (CBF) recommends items based on similarity between item features and user profiles. It relies on item metadata such as descriptions, categories, and tags (Lops et al., 2011).

Techniques:

- Feature Extraction: TF-IDF (Term Frequency-Inverse Document Frequency)

- Similarity Computation: Cosine similarity between item vectors

Example:
If a user rates "The Matrix" (Action, Sci-Fi) highly, CBF will recommend other Action/Sci-Fi movies like "The Terminator" or "Inception."

Limitations:

- Overspecialization (filter bubble)

- Limited feature representation

- Requires rich item metadata

## 2.4 Hybrid Recommendation Systems

Hybrid systems combine multiple techniques to overcome individual limitations (Burke, 2002).

| Approach | Description | Example |
| --- | --- | --- |
| Weighted | Combine scores with weighted average | Score = 0.6×CF + 0.4×CBF |
| Switching | Switch based on context | Use CF for known users, CBF for new users |
| Feature Combination | Combine features into single model | Use user-item interactions + item metadata |
| Meta-learning | Learn optimal combination | Train XGBoost on CF and CBF features |

Success Story:
Spotify's Discover Weekly uses a hybrid approach combining collaborative filtering (what similar users like), content-based filtering (audio features), and NLP (lyrics analysis). This generates 40 million+ personalized playlists weekly.

## 2.5 Evaluation Metrics

| Metric | Formula | Why Used | Practical Example |
| --- | --- | --- | --- |
| Precision@k | Relevant in Top k / k | Measures recommendation quality | "Precision@10 = 30% means 3 of 10 recommended items are liked by user" |
| Recall@k | Relevant in Top k / Total Relevant | Measures coverage | "Recall@10 = 40% means we found 4 of 10 relevant items in Top 10" |
| NDCG@k | Discounted Cumulative Gain | Prioritizes top positions | "A relevant item at #1 is more valuable than at #10 (higher score)" |
| RMSE | Root Mean Square Error | Measures prediction accuracy | "RMSE = 0.85 means predictions are ~0.85 stars from actual ratings" |

## 2.6 MLOps and Production ML

Modern ML projects require robust engineering practices (Sculley et al., 2015):

- Experiment Tracking: MLflow for logging parameters, metrics, and artifacts

- Pipeline Orchestration: ZenML for automating data processing, training, and deployment

- Model Monitoring: Detecting data drift and performance degradation

- Explainability: SHAP and LIME for interpretable recommendations

# 3. Problem Statement

## 3.1 Core Problem

E-commerce platforms and content streaming services face a significant challenge: users are overwhelmed by the sheer volume of available items, leading to decision paralysis, reduced engagement, and lower conversion rates.

Example:

- Amazon lists over 12 million products

- Netflix has 15,000+ titles

- Spotify has 100 million+ songs

Why Traditional Approaches Fail:

- Collaborative filtering fails to recommend new items (cold-start problem) and performs poorly for users with limited interaction history.

- Content-based filtering creates filter bubbles, recommending only items similar to what the user has already seen, reducing serendipity and discovery.

This Project's Solution:
Build a robust hybrid recommendation system that:

- Provides accurate, diverse, and personalized recommendations

- Handles cold-start scenarios using content-based fallback

- Achieves 15-20% improvement in Precision@10 over individual approaches

## 3.2 Inputs

The system will ingest the following data:

| Data Type | Description | Source |
| --- | --- | --- |
| User-Item Interactions | user_id, item_id, rating (1-5), timestamp | MovieLens 100K (100,000 ratings) |
| Item Metadata | item_id, title, release_date, 19 genres | MovieLens 100K (1,682 movies) |
| User Demographics | user_id, age, gender, occupation, zip_code | MovieLens 100K (943 users) |

## 3.3 Potential Challenges

| Challenge | Description | Impact |
| --- | --- | --- |
| Data Sparsity | Only 6.3% of possible user-item pairs have ratings | Reduces CF accuracy |
| Cold-Start | New users/items have no interaction history | Makes CF impossible for new entities |
| Scalability | Large datasets require efficient algorithms | Increases training and inference time |
| Explainability | Users need to trust recommendations | Black-box models reduce user adoption |
| Evaluation | Offline metrics may not correlate with online business metrics | May not capture real-world performance |

Example of Sparsity:
In MovieLens 100K: 100,000 ratings ÷ (943 users × 1,682 movies) = 6.3% density

## 3.4 Expected Outcomes

| Outcome | Description | Target |
| --- | --- | --- |
| Accurate Recommendations | High Precision@k and Recall@k | Precision@10 > 0.30 |
| Cold-Start Coverage | Recommendations for new users/items | Coverage > 80% |
| Model Explainability | SHAP/LIME explanations | Actionable insights |
| Production API | REST API for real-time serving | Latency < 500ms |
| Reproducible Pipeline | Orchestrated ML pipeline | One-click execution |

# 4. Project Objectives

| Objective | Description | Priority |
| --- | --- | --- |
| O1: Design and implement a hybrid recommendation system | Combine CF (SVD) and CBF (TF-IDF + Cosine Similarity) | High |
| O2: Build an end-to-end ML pipeline | Modular pipeline from data ingestion to deployment | High |
| O3: Implement production-grade API | FastAPI endpoint with low-latency predictions | High |
| O4: Integrate explainability | SHAP/LIME for recommendation transparency | Medium |
| O5: Apply MLOps best practices | MLflow tracking, ZenML orchestration, Docker | Medium |
| O6: Produce comprehensive documentation | Design decisions, implementation details, usage | High |

# 5. Scope and Deliverables

## 5.1 In-Scope

- Data preprocessing and EDA (pandas, matplotlib, seaborn)

- Collaborative filtering (Surprise library, SVD)

- Content-based filtering (scikit-learn, TF-IDF)

- Hybrid system (Weighted + Meta-learner with XGBoost)

- Evaluation framework (Precision@k, Recall@k, NDCG@k, RMSE)

- Experiment tracking (MLflow)

- Pipeline orchestration (ZenML)

- REST API (FastAPI)

- UI demo (Streamlit)

- Documentation and project report

## 5.2 Out-of-Scope

- Deep learning models (neural collaborative filtering) – future work

- Real-time streaming data processing

- A/B testing in production

- Advanced personalization with user context (location, time, device)

- Large-scale distributed training

## 5.3 Deliverables

| Deliverable | Format | Deadline |
| --- | --- | --- |
| Project Plan (Revised) | DOCX, PDF | 21-Aug-2026 |
| Data Pipeline & EDA | Code + Report | 27-Aug-2026 |
| Collaborative Filtering Model | Code + Evaluation | 3-Sep-2026 |
| Content-Based Model | Code + Evaluation | 10-Sep-2026 |
| Hybrid System | Code + Evaluation | 17-Sep-2026 |
| MLOps Pipeline & API | Code + Documentation | 24-Sep-2026 |
| Final Internship Report | DOCX | 30-Sep-2026 |
| Final Presentation | PPT | 30-Sep-2026 |
| GitHub Repository | URL | 30-Sep-2026 |

# 6. Detailed Timeline and Phased Approach

Phase 1: Project Planning and Research (Week 1: Aug 14-20)

| Day | Task | Description | Effort (hrs) |
| --- | --- | --- | --- |
| Day 1 (Aug 14) | Literature Review | Read 5-8 papers on SVD, CF, CBF, hybrid systems | 8 |
| Day 2 (Aug 15) | Dataset Analysis | Download MovieLens, understand structure, calculate sparsity | 4 |
| Day 3 (Aug 16) | Tool Selection | Evaluate pandas, surprise, scikit-learn, ZenML, MLflow | 6 |
| Day 4 (Aug 17) | Problem Definition | Refine statement, define success criteria, write objectives | 6 |
| Day 5 (Aug 18) | Technical Design | System architecture, component diagrams, data flow | 6 |
| Day 6-7 (Aug 19-20) | Write Project Plan | Complete all sections, format, review, submit | 12 |

Effort: ~42 hours | Deliverable: Project Plan (DOCX, PDF)

Phase 2: Data Engineering (Week 2: Aug 21-27)

| Day | Task | Description | Effort (hrs) |
| --- | --- | --- | --- |
| Day 1 | Data Ingestion | Load u.data, u.item, u.user into pandas DataFrames | 2 |
| Day 2 | Data Cleaning | Handle missing values, drop video_release_date, fill release_date | 6 |
| Day 3 | Exploratory Analysis | Visualize distributions, patterns, and trends | 8 |
| Day 4 | Feature Engineering | Create user, movie, and temporal features | 8 |
| Day 5 | Data Validation | Check data quality, verify transformations | 4 |
| Day 6-7 | Documentation | Write EDA report, update GitHub | 6 |

Effort: ~34 hours | Deliverable: Clean dataset, EDA report, data pipeline

Phase 3: Collaborative Filtering (Week 3: Aug 28 - Sep 3)

| Day | Task | Description | Effort (hrs) |
| --- | --- | --- | --- |
| Day 1 | Baseline Model | Implement popularity-based recommender | 4 |
| Day 2 | SVD Implementation | Train SVD using Surprise library, tune hyperparameters | 6 |
| Day 3-4 | Hyperparameter Tuning | Grid search: n_factors (10-100), reg (0.01-0.1), lr (0.001-0.01) | 8 |
| Day 5 | Evaluation | Compute RMSE, Precision@k, Recall@k, NDCG@k | 6 |
| Day 6 | Error Analysis | Analyze failure cases, document findings | 4 |
| Day 7 | Documentation | Write CF model report, update GitHub | 4 |

Effort: ~32 hours | Deliverable: CF model, evaluation report

Phase 4: Content-Based Filtering (Week 4: Sep 4-10)

| Day | Task | Description | Effort (hrs) |
| --- | --- | --- | --- |
| Day 1 | Feature Extraction | TF-IDF on movie genres, descriptions | 6 |
| Day 2 | Similarity Computation | Compute cosine similarity between items | 4 |
| Day 3 | User Profiling | Create user profiles from item interactions | 6 |
| Day 4 | Generate Recommendations | Evaluate CBF on test users | 6 |
| Day 5 | Evaluation | Compare performance against CF baseline | 4 |
| Day 6-7 | Documentation | Write CBF model report, update GitHub | 6 |

Effort: ~32 hours | Deliverable: CBF model, evaluation report

Phase 5: Hybrid System (Week 5: Sep 11-17)

| Day | Task | Description | Effort (hrs) |
| --- | --- | --- | --- |
| Day 1 | Weighted Hybrid | Combine CF and CB scores (weighted average: 0.3-0.7 range) | 6 |
| Day 2 | Switch Hybrid | Implement switching for cold-start detection | 4 |
| Day 3-4 | Meta-Learner Hybrid | Train XGBoost on CF and CBF features | 8 |
| Day 5 | Evaluation | Compare hybrid performance vs. individual models | 6 |
| Day 6 | Explainability | Integrate SHAP for recommendation explanations | 4 |
| Day 7 | Documentation | Write hybrid system report, update GitHub | 4 |

Effort: ~32 hours | Deliverable: Hybrid model, final evaluation report

Phase 6: MLOps and Deployment (Week 6: Sep 18-25)

| Day | Task | Description | Effort (hrs) |
| --- | --- | --- | --- |
| Day 1 | Pipeline Orchestration | Build ZenML pipeline with modular steps | 6 |
| Day 2 | Experiment Tracking | Set up MLflow for parameter and artifact logging | 4 |
| Day 3 | Model Serialization | Save optimized model artifacts (pickle, joblib) | 2 |
| Day 4-5 | REST API Development | Build FastAPI endpoint with request/response models | 8 |
| Day 6 | Streamlit UI | Create interactive demo with user input and recommendations | 4 |
| Day 7 | Documentation | Finalize all documentation, update GitHub | 4 |

Effort: ~28 hours | Deliverable: Working API, UI demo, Docker container

Phase 7: Finalization (Week 6 - Buffer: Sep 26-30)

| Day | Task | Description | Effort (hrs) |
| --- | --- | --- | --- |
| Day 1-3 | Internship Report | Compile complete report with all sections | 12 |
| Day 4 | PPT Preparation | Create presentation slides with visuals | 6 |
| Day 5 | GitHub Cleanup | Finalize code repository, tag final version | 4 |
| Day 6 | Viva Preparation | Review technical concepts, practice explanations | 3 |

Effort: ~25 hours | Deliverable: Internship Report, PPT, GitHub URL

Critical Path and Dependencies:

text

Data Acquisition → Data Cleaning → Feature Engineering →

→ Collaborative Filtering → Hybrid System → MLOps → Deployment

→ Content-Based Filtering →

Key Dependencies:

- Phase 2 must be completed before Phase 3 and Phase 4 (data quality is paramount)

- Phase 3 and Phase 4 must be completed before Phase 5 (hybridization requires both base models)

- Phase 5 must be completed before Phase 6 (deployment requires finalized model)

# 7. Key Milestones

| Milestone | Target Date | Deliverable | Status |
| --- | --- | --- | --- |
| M1: Project Plan Approved | 21-Aug-2026 | Project Plan DOCX (Revised) | Pending |
| M2: Data Pipeline Complete | 27-Aug-2026 | Clean dataset, EDA report | Pending |
| M3: Baseline CF Model | 3-Sep-2026 | CF model + evaluation | Pending |
| M4: Content-Based Model | 10-Sep-2026 | CBF model + evaluation | Pending |
| M5: Hybrid System Complete | 17-Sep-2026 | Hybrid model + final evaluation | Pending |
| M6: API Deployed | 25-Sep-2026 | FastAPI endpoint, UI demo | Pending |
| M7: Final Submission | 30-Sep-2026 | Report, PPT, GitHub URL | Pending |

# 8. Resource Requirements

## 8.1 Software and Libraries

| Category | Tools/Libraries | Version | Purpose |
| --- | --- | --- | --- |
| Language | Python | 3.9+ | Core programming |
| Data Processing | Pandas, NumPy | Latest | Data manipulation, numerical operations |
| Data Visualization | Matplotlib, Seaborn, Plotly | Latest | Charts, graphs, interactive plots |
| Machine Learning | Scikit-learn, XGBoost | Latest | TF-IDF, cosine similarity, meta-learner |
| Collaborative Filtering | Surprise, Implicit | Latest | SVD, ALS, model training |
| Experiment Tracking | MLflow | Latest | Logging parameters, metrics, artifacts |
| Pipeline Orchestration | ZenML | Latest | End-to-end ML pipeline automation |
| API Development | FastAPI, Uvicorn | Latest | REST API serving recommendations |
| UI Demo | Streamlit | Latest | Interactive user interface |
| Explainability | SHAP, LIME | Latest | Model interpretability |
| Containerization | Docker | Latest | Application packaging and deployment |
| Version Control | Git, GitHub | N/A | Code management |

## 8.2 Computational Resources

| Resource | Specification | Purpose | Cost |
| --- | --- | --- | --- |
| Development Machine | 16GB RAM, 4+ cores, Windows 11 | Local development, small experiments | Existing |
| Cloud GPU | Google Colab Free / Kaggle | GPU-accelerated training (XGBoost) | Free |
| Cloud VM (Optional) | AWS EC2 / GCP t2.medium | Deployment testing | ~$0.05/hr |
| Storage | GitHub (1GB free) | Code and small datasets | Free |

Recommendation: Use Google Colab for XGBoost training if local machine is slow.

## 8.3 Data Resources

| Dataset | Size | Source | License |
| --- | --- | --- | --- |
| MovieLens 100K | 100,000 ratings, 1,682 movies, 943 users | GroupLens | Research-friendly |
| MovieLens 1M (Optional) | 1,000,000 ratings | GroupLens | Research-friendly |

## 8.4 Human Resources

| Role | Responsibility | Person |
| --- | --- | --- |
| ML Engineer | Full development and implementation | Tirumala Karthik |
| Mentor/Supervisor | Guidance and evaluation | Keerthi |

# 9. Risk Management

## 9.1 Risk Identification and Mitigation

| Risk | Probability | Impact | Mitigation Strategy | Contingency Plan |
| --- | --- | --- | --- | --- |
| R1: Data Quality Issues | Medium | High | Implement thorough EDA; use df.isnull().sum() daily; handle missing values with median/mean imputation | Use synthetic data from sklearn.datasets; alternative dataset (MovieLens 1M) |
| R2: Model Underperformance | Medium | High | Establish baseline early (popularity-based); iterative improvement; use 5-fold cross-validation | Switch to simpler models (linear regression, KNN); ensemble methods for improvement |
| R3: Computational Limitations | Medium | Medium | Use Google Colab/Kaggle for large experiments; optimize code efficiency | Reduce dataset size to 50,000 samples; use precomputed features |
| R4: Integration Complexity | Medium | Medium | Modular design; test each component separately; use ZenML for structured pipeline | Simplify integration; use proven libraries; reduce number of components |
| R5: Time Constraints | High | High | Strict adherence to weekly plan; prioritize MVP features (CF + CBF + Basic API) | Cut non-essential features; focus on core system; extend buffer week |
| R6: Dataset Size | Low | Medium | Use MovieLens 100K for prototyping; scale to 1M if ahead of schedule | Use preprocessed/subsampled data; optimize memory usage |
| R7: Deployment Issues | Medium | Medium | Deploy locally first; use Docker for containerization; test API with curl and Postman | Use simpler deployment (local API only); use Hugging Face Spaces |
| R8: Viva Preparation | Medium | High | Document everything; review weekly; create presentation early | Create comprehensive notes; practice explanations with peers |

## 9.2 Risk Monitoring Plan

- Weekly Review: Every Friday, assess progress against timeline

- Issue Log: Maintain log of encountered issues and resolutions

- Mentor Check-in: Weekly sync with internship supervisor (Keerthi)

- Buffer Time: Reserve Sep 26-30 as buffer for finalization and viva preparation

- Progress Tracking: Use Trello/GitHub Projects for task tracking

# 10. Strategic Roadmap for Implementation

## 10.1 Phased Implementation Strategy

Phase 1: Foundation (Week 1-2)

- Establish solid foundation with thorough planning and data understanding

- Critical success factor: Clean, well-understood data

- Key decision: Choose dataset and architecture

Phase 2: Core Algorithms (Week 3-4)

- Build individual components (CF and CBF) independently

- Critical success factor: Strong baseline performance

- Key decision: Select best-performing CF and CBF configurations

Phase 3: Integration (Week 5)

- Hybridize the two approaches

- Critical success factor: Hybrid outperforms individual models

- Key decision: Hybridization strategy (Weighted vs. Meta-learner)

Phase 4: Productionization (Week 6)

- Package the system for deployment

- Critical success factor: Functional API with reasonable latency (<500ms)

- Key decision: Deployment platform (local vs. cloud)

Phase 5: Finalization (Week 6 Buffer)

- Complete documentation and prepare for evaluation

- Critical success factor: Comprehensive report and viva readiness

## 10.2 Key Technical Decisions

| Decision Point | Options | Decision | Rationale |
| --- | --- | --- | --- |
| CF Algorithm | SVD, ALS, NMF | SVD | Simplicity, well-documented, good performance |
| CBF Vectorization | TF-IDF, Word2Vec, BERT | TF-IDF | Simplicity, interpretability, works well with short text |
| Hybridization | Weighted, Switching, Meta-learner | Weighted + Meta-learner | Weighted is simple; Meta-learner for advanced comparison |
| Pipeline Framework | ZenML, Kedro, Custom | ZenML | Good for beginners, integrates with MLflow |
| API Framework | FastAPI, Flask | FastAPI | Modern, fast, auto-documentation |
| UI Demo | Streamlit, Gradio | Streamlit | Simple, Python-native, good for demos |

## 10.3 Success Metrics

| Metric | Target | Rationale |
| --- | --- | --- |
| Precision@10 | >0.30 | Industry-standard; demonstrates relevance |
| Recall@10 | >0.20 | Ensures coverage of relevant items |
| NDCG@10 | >0.50 | Accounts for ranking quality |
| RMSE | <0.90 | Accurate rating predictions |
| Cold-Start Coverage | >80% | New users/items get recommendations |
| API Latency | <500ms | Usable in production |
| Model Improvement | >15% over baseline | Hybrid system must demonstrate value |

# 11. Success Criteria and Evaluation Metrics

## 11.1 Technical Success Criteria

- Functional System: Complete pipeline from data ingestion to API serving recommendations

- Model Performance: Hybrid model outperforms both CF and CBF individually by at least 15% in Precision@10

- Cold-Start Handling: System provides recommendations for users with <5 interactions

- Reproducibility: Full pipeline can be run from scratch to reproduce results

- Documentation: Clear, comprehensive documentation covering all aspects

## 11.2 Academic Evaluation Criteria

| Criterion | Description | Weight |
| --- | --- | --- |
| Project Plan | Clarity, completeness, feasibility | 10% |
| Technical Implementation | Code quality, functionality, innovation | 30% |
| Internship Report | Structure, clarity, depth of content | 30% |
| PPT Presentation | Visual design, clarity, flow | 10% |
| Viva Performance | Conceptual understanding, articulation | 20% |

# 12. Conclusion

This project plan outlines a comprehensive 6-week implementation of a Hybrid Recommendation System, designed to meet the requirements of the mandatory academic summer internship. The project leverages a strong theoretical foundation in machine learning algorithms, applying them to build a practical, production-ready system.

Key Strengths:

- Real-world problem with measurable business impact

- Specific, achievable targets (Precision@10 > 0.30, RMSE < 0.90)

- Comprehensive risk management with clear contingency plans

- Professional MLOps practices (MLflow, ZenML, Docker)

- Clear evaluation metrics with practical examples

The phased approach ensures systematic progress, with clear milestones and deliverables at each stage. The hybrid system addresses the core challenges of recommendation systems—cold-start and data sparsity—by combining collaborative and content-based filtering.

Upon completion, this project will serve as a strong portfolio piece, demonstrating end-to-end ML engineering capabilities, theoretical understanding, and the ability to deliver a functional product with professional documentation.

Next Steps:

- Begin data engineering (Week 2) immediately after project plan approval

- Follow the detailed daily schedule

- Maintain regular GitHub commits

- Weekly mentor check-ins for feedback

# 13. References

- Burke, R. (2002). Hybrid recommender systems: Survey and experiments. User Modeling and User-Adapted Interaction, 12(4), 331-370.

- Herlocker, J. L., Konstan, J. A., Terveen, L. G., & Riedl, J. T. (2004). Evaluating collaborative filtering recommender systems. ACM Transactions on Information Systems, 22(1), 5-53.

- Koren, Y. (2009). The BellKor solution to the Netflix Grand Prize. Netflix Prize Documentation.

- Koren, Y., Bell, R., & Volinsky, C. (2009). Matrix factorization techniques for recommender systems. Computer, 42(8), 30-37.

- Lops, P., de Gemmis, M., & Semeraro, G. (2011). Content-based recommender systems: State of the art and trends. In Recommender Systems Handbook (pp. 73-105). Springer.

- Resnick, P., Iacovou, N., Suchak, M., Bergstrom, P., & Riedl, J. (1994). GroupLens: An open architecture for collaborative filtering of netnews. Proceedings of CSCW, 175-186.

- Sarwar, B., Karypis, G., Konstan, J., & Riedl, J. (2001). Item-based collaborative filtering recommendation algorithms. Proceedings of WWW, 285-295.

- Sculley, D., Holt, G., Golovin, D., Davydov, E., Phillips, T., Ebner, D., ... & Young, M. (2015). Hidden technical debt in machine learning systems. Advances in Neural Information Processing Systems, 28, 2503-2511.

- Zhang, S., Yao, L., Sun, A., & Tay, Y. (2019). Deep learning based recommender system: A survey and new perspectives. ACM Computing Surveys, 52(1), 1-38.